## Sheet 1 - Table 1
Biggest Ever Blokes' Lunch Marketing Timeline template
| Activity | Type | Audience | Date | Duration
Online | PCFA.org.au website - events calendar | Online | General | Send to PCFA as soon as possible - 4 to 6 months prior to event | Duration of campaign
| Other websites | Online | Directed from other activities/material |  | Duration of campaign
| Email link in signature | Online | Business contacts | 4 to 6 months prior - all committee members | Duration of campaign
Social Media | Paid Facebook ads | Online | General | 4 - 6 months prior | Duration of campaign
| Facebook/Twitter/Instagram/LinkedIn posts | Online | General | Commence 4 months prior, during event and post event thank yous | Weekly or fortnightly
Internal Comms - Committee | Email to all contacts | Email | Staff | 4 - 6 months prior to event eg "Save the date" once date/venue confirmed | 2-3 times
| Volunteers | Poster and flyer | Volunteers/Interns | 4 to 6 months prior | Duration of campaign
External | Local noticeboards | Poster | General | 4 to 6 months prior | Duration of campaign
| DL flyer drops | Flyer | General | 4 to 6 months prior
Publications | Local newspapers | Advert and editorial |  | 4 to 6 months prior | Duration of campaign
| APEXian Newsletter | editorial | Apex members | 4 to 6 months prior | Once
Media | Radio | Radio | General | 4 to 6 months prior | Duration of campaign
| TV | TV | General | 4 to 6 months prior | Duration of campaign